## Overview
Step 0 | Create a new copy of this document
This is a blank template. Please do not edit this document directly. Create a copy.
Step 1 | Work Breakdown
There are three hierarchy levels to define a work breakdown. These could be thought of as Epic/Feature/Story.
Break down to as much detail as you can, the more the better.
Some times, you don't have more detail, that is fine. Try to have at least 10 line items in your estimate.
If you are getting down to the level of tasks that will only take a few minutes to accomplish, you are going too deep.
If you are inserting new rows, ensure you copy the equations for Expected Case, STD Dev, and Variance into the rows.
Step 2 | Ranged Effort Estimate
The range from best case to worst case should be:
Estimated in Hours
Account for time required to get to "Done" and not just "Code Complete"
Assume a generic resource that has average skillsets required to accomplish the task
Give a range that you would be 90% confident is achievable. This may result in very large ranges - thats good! We want to know where those are.
4 hours to 400 hundred hours may be a perfectly valid estimate.
If we knew perfectly what needed to be done, it probably wouldn't be worth doing.
There are going to be areas we don't know, or have a large degree of uncertainty.
Step 3 | Interpretation
The duration and effort estimate numbers will give you a starting point to develop a staffing plan.
The duration should be considered a "do not go under" number. While work may take more time, it will almost never take less.
For the duration specified, add resources to a staffing plan to account for the estimated effort until parity is achieved.
There may be known schedule dependencies that cannot be estimated in the planned activities - like Holidays, PTO, Ramp Up - the staffing plan is where these are accounted for.
There is an example staffing plan, but it is mostly a manual process and will need to be created for each case.
Step 4 | Refinement & Presentation
These worksheets are not for business consumption, they are worksheets for technical teams to sanity check their plans.
The numbers and plans that come out of this may require further refinement or tweaking based on SME knowledge of the work.
At the end of the day, we are making a guess, all of us are bad at predicting the future. This is meant to identify and communicate planned effort and risks.

## Worksheet
Level 1 | Level 2 | Level 3 | Notes | Best Case | Worst Case | Expected Case | STD Dev | Variance
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | - | 0
|  |  | STD Dev | - | - |  | - | 0
|  |  | Effort |  |  |  |  | 0 | hours
[8 empty] | 0 | staff weeks
|  |  | Duration |  |  |  |  | 0 | weeks

## Worksheet Example
Level 1 | Level 2 | Level 3 | Notes | Best Case | Worst Case | Expected Case | STD Dev | Variance
Layouts & schemas | [5 empty] | 0 | 0 | 0
| Page 1 | 7 components potential horizontal scroll feature |  | 80 | 120 | 93.2 | 15.3846 | 236.6864
| Page 2 | 8 components |  | 70 | 200 | 112.9 | 50 | 2500
| Page 3 | 7 components potential horizontal scroll feature and accordion | Accordion is hard | 100 | 320 | 172.6 | 84.6154 | 7159.7633
| Page 4 | 4 components |  | 40 | 80 | 53.2 | 15.3846 | 236.6864
| Page 5 | 8 components |  | 60 | 90 | 69.9 | 11.5385 | 133.1361
| Nav & Footer |  | Need more info | 80 | 160 | 106.4 | 30.7692 | 946.7456
[6 empty] | 0 | 0 | 0
Contentstack | [5 empty] | 0 | 0 | 0
| Environement & Language Config |  |  | 4 | 16 | 7.96 | 4.6154 | 21.3018
| Translations (admin activities) |  | Dependent on another team | 80 | 100 | 86.6 | 7.6923 | 59.1716
Documentation & Handoff | [5 empty] | 0 | 0 | 0
| Q&A |  |  | 40 | 100 | 59.8 | 23.0769 | 532.5444 |  | Staffing Plan
| Reame, docs |  |  | 16 | 30 | 20.62 | 5.3846 | 28.9941 |  |  |  | Weeks
[10 empty] | Discipline Required |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | Total | 570 | 1216 | 783.18 | - | 11855.0296 |  | Scrum Master | 84 | 6 | 6 | 6 | 6 | 6 | 6 | PI Plan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  | STD Dev | - | - |  | - | 108.8808 |  | Lead Dev | 432 | 36 | 36 | 36 | 36 | 36 | 36 | PI Plan | PTO | PTO | 36 | 36 | 36 | 36 | 36 | 36
|  |  | Effort |  |  |  |  | 892.0608 | hours | Associate Dev | 504 | 36 | 36 | 36 | 36 | 36 | 36 | PI Plan | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
[8 empty] | 24.7795 | staff weeks | QA | 140 | 8 | 8 |  |  |  |  | PI Plan | 8 | 8 | 8 | 20 | 20 | 20 | 20 | 20
|  |  | Duration |  |  |  |  | 11 | weeks | Total Hours | 1160 | 86 | 86 | 78 | 78 | 78 | 78 | 0 | 50 | 50 | 86 | 98 | 98 | 98 | 98 | 98
*** scroll to the right for staffing plan ***
Notes
Weeks 1 & 2 will be mostly ramp up
Week 7 is PI planning
Week 8 & 9 our lead is on PTO
QA activities will ramp up near the end
36 hours per week max were set as an estimate expectation on the variables tab

## Variables
Duration Multiplier | 3.5
STD Dev Divisor | 2.6
Billable hours/week | 36
Ecpected Case Multiplier | 0.33